## Slide 1: South African – Flemish (SAF) Development Programme DGOS-attachés 2003
VVOB

## Slide 2: SAF Development Programme Objectives
Clarity on the role of Flemish partners (aBB & VVOB) involved in development co-operation
Overview of the Flemish-South African Indicative Development Program
Flanders policy on Cross Sectoral Themes (CST)
Clarity on the role of South African National Treasury in the whole process
Explanation of the Project Cycle Management (PCM)
How to do the financial and other reporting on the project
Practicalities

## Slide 3: SAF Development Programme Taakverdeling aBB & VVOB
SA Partners
VVOB
aBB
aBB = Administratie Buitenlands Beleid
= Administration for foreign affairs
(Flanders Foreign Policy Arm)
VVOB = Vlaamse Vereniging voor Ontwikkelingssamenwerking en Technische Bijstand
= Flemish Office for International Co-operation and Technical Assistance
Flanders
Flanders = a regional state in the Federal Kingdom of Belgium with international powers

## Slide 4
Programming
Identification
Formulation
Financing
Implementation
Evaluation
Project Cycle Management (PCM) Steps

## Slide 5: Project Cycle Management (PCM) aBB & VVOB primary responsibilities
Primary responsibilities | aBB | VVOB
Programming |  | 
Identification |  | 
Formulation |  | 
Financing & agreement |  | 
Implementation |  | 
Monitoring |  | 
Evaluation |  | 

## Slide 6
Project Cycle Management (PCM) Why PCM?
Unclear strategic framework
Supply driven projects
Poor analysis of situation
Activity-orientated planning
Non-verifiable impact
Disbursement pressure
Short-term vision
Imprecise proj. documents
Experiences
PCM
Sectoral approach
Demand driven approach
Improved analysis
Objective orientated planning
Verifiable impact
Emphasis on quality
Focus on sustainability
Standardized formats

## Slide 7
Project Cycle Management (PCM) Document phases in project cycle
Programming
Identification
Formulation
Financing
Implementation
Evaluation
Flanders – SA indicative co-operative
development programme
Budget
proposal
Identification
proposal
Evaluation
reports
Action Plans
Progress monitoring
Result monitoring
Decision
Project
agreement
Mid term
Review reports
Logical
framework
Identification
report
ToR
ToR
Detailed budgets
Strategy document jointly developed between aBB and SA partners

## Slide 8
Project Cycle Management (PCM) Cross Sectoral Themes (CST’s)
FLANDERS POLICY ON CROSS SECTORAL THEMES
1. HIV/AIDS
Study possible threat to viability of projects
Focus on prevention & awareness
2. Gender
Gender equality/ affirmative action
Women empowerment: training, education & capacity building
Gender & HIV/AIDS
3. Sustainable Development
Integration of environmental, social and economic issues in projects
SD in all sectors of development
Indicators
Instruments
Checklists

## Slide 9
PCM - Procedures Identification phase
Administrative Organisation
Project Proposer
Potential project implementer
VVOB - SA Representative
Various Stakeholders
SA partners
Flemish partners
Facilitator (eventually)
Flanders Technical experts if necessary?

## Slide 10
Programming
Identification
Formulation
Financing
Implementation
Evaluation
PCM - Procedures Implementation & Monitoring phases

## Slide 11
PCM - Procedures Implementation & Monitoring phases
Objective:
Involved stakeholders:
Project team, partner institutions, beneficiaries,…
Actions:
To achieve the project’s purpose
call for bids & contracting with suppliers
Detail programming & implementation of activities
Budgeting & management of project finances
Re-orientation of implementation, if necessary
Monitoring & mid-term evaluation
Outputs:
Completed project
Implementation

## Slide 12
PCM - Procedures Implementation & Monitoring phases
Monitoring types
Progress monitoring
Result monitoring
Follow up of operational planning & financial means
Looks at activities
Prepared by SA partners & reviewed/ completed by the VVOB
Verifies the output & degree of realisation
Looks at the results
Prepared by SA partners & reviewed/ completed by Flanders expert & the VVOB

## Slide 13
PCM - Procedures Implementation & Monitoring phases
Implementation & Monitoring tasks
SA Partners
VVOB
Thorough implementation of the project
Operational responsibility
3-monthly PMR (narrative + logframe excel file)
Yearplanning
Constant feedback about the running of the project
3-monthly progress monitoring report based on PMR provided by SA partner
6 monthly field visits to the project site(s)
Day-to-day availability for nay kind of assitance (except finances)
Organization of exchanges, short term missions, etc.

## Slide 14
PCM - Procedures Implementation & Monitoring phases
Progress Monitoring Reporting Procedure
SA partner
Flanders
Writes 3-monthly narrative PM Report + Logframe
Writes 3-monthly PM report based on SA reporting
1
2
Reads Flanders report
3
Report sent to VVOB Flanders and concerned departments
Agrees
Does not agree
Partner writes his own report
4b
4a
Both reports are reviewed by expert at the time of the result monitoring or mid-term review and advice is given to SAP & Flanders
Decision on the continuation or discontinuance of the funding of the project
6
5

## Slide 15
Programming
Identification
Formulation
Financing
Implementation
Evaluation
PCM - Procedures Evaluation phase

## Slide 16
PCM - Procedures Evaluation phase
Objective:
Involved stakeholders:
External expert & VVOB in full collaboration with all the partners and project stakeholders
Actions:
To assess the project results & effects in relation to its objectives
Draft ToR for mid-term evaluation
Carry out mid-term evaluation using appropriate methodology
Assess relevance, efficiency, effectiveness, impact and sustainability of the project
Make recommendations as appropriate
Outputs:
Mid-term evaluation report with recommendations at different levels
Mid-Term evaluation (after 11/2 year for 3 years projects only)