Assessing the Quality
of a Financing Proposal

This document is used as resource material in the PCM training programme. It is not an official document, and remains in draft form. It is intended to provide guidance in applying the principles of PCM to assist in assessing the quality of project documents, and in particular, Financing Proposals.

Assessing the Quality of a Financing Proposal

- Training and Helpdesk Services in Project Cycle Management

Table of Contents

The Purpose of Quality Assessment	2

Quality Assessment Parameters	2

1.	Relevance	2

1.1	Are the beneficiaries clearly identified?	2

1.2	Are the problems of the beneficiaries described sufficiently?	2

1.3	Is the problem analysis sufficiently comprehensive?	2

1.4	Do the Overall Objectives explain why the project is important for society?	2

1.5	Is the Project Purpose defined in terms of benefits to the beneficiaries?	2

1.6	Has the need for the Results been demonstrated ?	2

2.	Feasibility	2

2.1	Will the Project Purpose contribute to the Overall Objectives (if the Assumptions hold)?	2

2.2	Are the Results described as services to be delivered to the target group?	2

2.3	Will the Project Purpose be achieved if the Results were delivered?	2

2.4	Are the means sufficiently justified by quantified objectives	2

2.5	Have important external conditions been identified?	2

2.6	Is the probability of realisation of the Assumptions acceptable?	2

2.7	Will the implementing agencies be able to implement the project?	2

3.	Sustainability	2

3.1	Will the relevant authorities have a supportive policy after the project has ended?	2

3.2	Is the technology appropriate for the local conditions?	2

3.3	Will the ecological environment be preserved during and after the project?	2

3.4	Will there be adequate ownership of the project by the beneficiaries?	2

3.5	Will all beneficiaries have adequate access to benefits and production factors during and after the project?	2

3.6	Will the implementing agencies be able to provide follow-up after the project?	2

3.7	Is the financial and economic analysis reliable? Does it confirm that the ‘incremental project’ is efficient, effective, viable, relevant and that its effects are positive?	2

Using the Quality Assessment Tool to Identify Information Needs	2

Quality Rating Sheet for Financing Proposals	2

Assessing the Quality of a Financing Proposal

## The Purpose of Quality Assessment

During the Identification and Formulation stages of the project cycle, a major task of project cycle managers within the Commission and co-operating Ministries of partner countries is to ensure the quality of project design. By assessing the quality of project design, project cycle managers are able to identify logical inconsistencies, information gaps and other problems with the financing proposal, and are thus able to formulate questions about the project which can be clarified subsequently, e.g. by discussion with the partner countries or an additional short study.

A blank information sheet is appended where issues requiring further clarification can be recorded. Also appended is a "Quality Rating Sheet" on which you can summarise your appreciation of the quality of the Financing Proposal.

## Quality Assessment Parameters

Under PCM there are three main parameters by which financing proposals should be assessed: Relevance, Feasibility and Sustainability.

| - Relevance relates to the importance of the problems to be addressed by the project, and starts with determining for whom the project is relevant. At the project purpose level, the project should address the specific problems of the target group (for example, declining revenues of small scale agricultural producers). At the overall objectives level the project should address the related but wider problems of society as a whole (for example, declining standards of living in rural areas). |  |
| --- | --- |
| - Feasibility relates to whether the project objectives can be effectively achieved. This requires an assessment of the coherence of the project’s intervention logic and assumptions (e.g. if Results are delivered, and Assumptions hold true, will the Project Purpose be achieved?) and of the capability of the implementing agency to mobilise the necessary resources and expertise to undertake project activities within the time required. |  |
| - Sustainability relates to whether project benefits will continue to flow after the period of external assistance has ended. Although actual sustainability cannot be assessed ex ante, prospects for sustainability can be assessed by determining the extent to which mechanisms have been incorporated into project design to address the key factors which have influenced sustainability in the past. |  |

### Relevance

A project is designed and implemented in order to solve certain problems faced by people. The people whose problems are to be resolved are the beneficiaries of the project. The relevance of a project is the degree to which their real problems are addressed by the proposed intervention. Six key questions need to be posed when assessing if a project is relevant.

#### Are the beneficiaries clearly identified?

A clear description of beneficiaries should, at a minimum, include a statement of their economic and social roles/positions and their geographical location. Other information may be relevant, depending on the project, such as educational/skills levels, ownership and/or access to resources, etc. A gender breakdown of this information is vital, in order to ensure that the needs of women and men are addressed by the project. Information on age, ethnicity or other social characteristics may also be required.

##### Scoring indicators: The beneficiaries have been clearly identified…

|  | when... |
| --- | --- |
| fully | Beneficiaries have been described in detail, including socio-economic roles and positions, geographical location, gender breakdown and mention of other key factors. |
| fairly | The description includes key socio-economic information, geographical location and gender breakdown, but lacks detail. |
| hardly | Some elements only are specified. |
| not at all | No specific roles or locations mentioned. |

#### Are the problems of the beneficiaries described sufficiently?

Problems are factual descriptions of existing negative situations in a particular part of society. Very often, financing proposals only describe macro-economic problems, or limit themselves to the problems of implementing institutions or service delivery organisations. In order to verify the project’s relevance, the problems faced by the beneficiaries in relation to the project’s area of intervention should be analysed in detail, and the relative importance of these problems explained. Different beneficiaries (in particular men and women) may have different problems, and therefore both global and group-specific problems should be mentioned.

##### Scoring indicators: Problems of beneficiaries are described sufficiently…

|  | when... |
| --- | --- |
| fully | Problems of beneficiaries have been described in detail, including information on the specific problems faced by the different beneficiary groups/sub-groups. |
| fairly | Problems of beneficiaries have been described in reasonable detail, but information on specific problems of different groups is incomplete or missing. |
| hardly | Few problems faced by beneficiaries have been described. |
| No | No problems from the viewpoint of beneficiaries are stated. |

#### Is the problem analysis sufficiently comprehensive?

A comprehensive problem analysis defines the problems of the beneficiaries (see above) and other relevant problems, but also explains why these problems occur, or why they persist. This requires a systematic analysis of all relevant problems and their causes. Many proposals discuss problems in a haphazard way, without explaining the underlying reasons for the persistence of the main problems. These are ‘gaps’ in the problem analysis. Sometimes problems are not formulated as existing negative situations, but as ‘absent solutions’ (often phrased as a ‘lack of..’ something). They are described as the solutions which are not there, and these give rise to the so called shopping list projects - what is needed is widgets because there is a lack of widgets. The effect is that the existing situation is not researched, but instead solutions are proposed. Sometimes problems are described in very general terms (e.g. ‘poor management’), which give no indication about what is going wrong.

##### Scoring indicators: The problem analysis is comprehensive…

|  | when... |
| --- | --- |
| fully | The causes of the problems of beneficiaries have been researched, and the relations with service delivery agencies and other actors in the environment are clearly presented. |
| fairly | The causes of most problems of beneficiaries have been analysed on a reasonable level of detail. |
| hardly | Some problems are mentioned, but have not been researched. Some areas of interest for beneficiaries or delivery organisations have not been researched. |
| not | Problems mentioned are either absent solutions (lack of...), very large categories or personal opinions. Main areas of interest have not been researched. |

#### Do the Overall Objectives explain why the project is important for society?

Overall Objectives indicate the longer term benefits which can be expected from the project. The extent to which these benefits can be shared by others than the direct beneficiaries can be a measure for the relevance of the project to society in general. However, the Overall Objectives should also state the longer term benefits for the beneficiaries. This seems obvious, but it is often omitted. It should also become apparent how the Overall Objectives relate to the sectoral policies of the government, and to the sectoral objectives stated in the Indicative Programme, Country Strategy Paper, etc.

##### Scoring indicators: Overall Objectives explain why the project is important to the parties involved…

|  | when... |
| --- | --- |
| fully | The beneficiaries and other groups in society find longer term benefits in the project, and the project fits within the sectoral policies of the Government and the sectoral objectives stated in the Indicative Programme, Country Strategy Paper, etc. |
| fairly | Beneficiaries find longer term benefits in the project and the project fits within the sectoral policies of the Government and the sectoral objectives stated in the Indicative Programme, Country Strategy Paper, etc. |
| hardly | Only one of the two elements above is mentioned. |
| not at all | Overall Objectives are not longer term benefits for the beneficiaries. |

#### Is the Project Purpose defined in terms of benefits to the beneficiaries?

Projects are intended to deliver sustainable benefits to their intended beneficiaries. A benefit can be described as having been received when the beneficiaries’ status is improved in terms of one or more of their socio-economic characteristics. This can relate to the economic environment (income, employment, etc.) the social environment (living conditions, hygiene, nutrition, health, etc.) or even the very personal environment (absence of stress, fulfilment of aspirations, etc.). These benefits are derived by the beneficiaries as a result of their utilisation of project services.

The Project Purpose should not describe the delivery of the service that creates the benefit, nor should it describe the utilisation of the service by the beneficiaries. It should describe the benefits which result from utilisation. For example, if a health project delivers improved access to vaccinations for under-fives, the Project Purpose should not describe the increased number of children vaccinated, but the improved health status which results from this. In relation to the gender disaggregated problem analysis, it is important to separately analyse the benefits to be received by men and women.

##### Scoring indicators: The Project Purpose is formulated as a benefit for the beneficiaries…

|  | when... |
| --- | --- |
| fully | The PP describes a direct benefit to be derived from the project by the beneficiaries as a result of using project services. |
| fairly | The PP describes a direct benefit to be derived from the project by the beneficiaries, but its linkage to project services is not fully explained. |
| hardly | The PP describes the utilisation of project services by the beneficiaries, rather than a direct benefit. |
| not at all | The PP describes the delivery of services by the project. |

#### Has the need for the Results been demonstrated ?

Most projects are designed to deliver services to particular target groups. The need for these services should be researched thoroughly in the formulation phase of the project, or, even better, the services should be designed after we know why problems persist. This is not always done, meaning that the need for the services is not apparent. It is vitally important that demand for project services is analysed for both men and women (and where necessary to other groups) in order to ensure the relevance of Results to all beneficiaries. Note that Results can be targeted at the beneficiaries, but also at intermediate service delivery groups; e.g. teachers receiving teacher training in an education project.

##### Scoring indicators: The need for the Results has been clearly demonstrated…

|  | when... |
| --- | --- |
| fully | Beneficiaries (or other target groups) have expressed a demand for all of the Results to be delivered by the project. |
| fairly | Beneficiaries (or other target groups) have expressed a demand for most of the Results to be delivered by the project. |
| hardly | Beneficiaries (or other target groups) have expressed a demand for some of the Results to be delivered by the project. |
| not at all | Beneficiaries (or other target groups) have not expressed a demand for any of the Results to be delivered by the project. |

### Feasibility

An assessment of feasibility asks the question - can this idea be realised? Three aspects are assessed: the logical consistency of the project (does it make sense?); whether the identified risks are acceptable; and whether the capacity exists to implement it.

#### Will the Project Purpose contribute to the Overall Objectives (if the Assumptions hold)?

The first check of the logic is whether the Project Purpose would indeed contribute to the Overall Objectives. In order to check this, the proposal should present evidence from past experience that there is a clear linkage between the Project Purpose and Overall Objectives. Sometimes the relation is rather obvious, but is also happens that completely unrealistic forecasts are being made without any supporting data.

##### Scoring indicators: The Project Purpose contributes to the Overall Objectives…

|  | when... |
| --- | --- |
| fully | Previous experience (in other projects or regions) has shown a strong causal relationship between the Project Purpose and Overall Objectives. |
| fairly | Previous experience (in other projects or regions) has shown a sufficient causal relationship between the Project Purpose and Overall Objectives. |
| hardly | No supporting data is presented, but it does make sense. |
| not at all | No data presented; it does not make sense. |

#### Are the Results described as services to be delivered to the target group?

Before checking whether the Results are sufficient in order to achieve the Project Purpose, we can check whether the Results have been formulated as services. Very often, the Results are described as activities (e.g. ‘training provided’) without specifying what will be delivered (the client does not buy the training, but the skill or the competence) and neither to whom. If the Results are not properly described, it is very difficult to check any logic, simply because it could mean anything at all. A service should be specified to such an extent that it can be delivered in reality and against a calculable cost, in other words it should be ‘marketable’.

##### Scoring indicators: Results are described as services to be delivered…

|  | when... |
| --- | --- |
| fully | All Results are formulated as services to be delivered to the target group, and are specified in sufficient detail. |
| fairly | Some Results are formulated as services to be delivered to the target group, and are mostly specified in sufficient detail. |
| Hardly | Some Results are formulated as services to be delivered to the target group, but specified only in general terms. |
| Not at all | Results are formulated as activities and not as services. |

#### Will the Project Purpose be achieved if the Results were delivered?

The results-to-purpose linkage is the key linkage in the project’s intervention logic as it describes the relationship between what the project will deliver (Results) and the benefits to be received by the target group (the Project Purpose). While project management can be held accountable for delivery of the Results, achievement of the Project Purpose requires a beneficiary response - i.e. a willingness/ability to use project services, followed by experience of a benefit. Information must thus be presented to demonstrate not only that the beneficiaries are willing or able to use project services (see 1.6 above), but also that this utilisation is likely to produce a benefit. This latter point can be demonstrated if the beneficiaries or evidence from past projects confirms that the Results remove the causes of the main problems underlying the Project Purpose. For example, a vocational training project may succeed in the result of upgrading the skills of its target group; but if insufficient job vacancies exist then its Project Purpose of increased employment of the target group will not be achieved.

##### Scoring indicators: The Project Purpose will be achieved if the Results are delivered…

|  | when... |
| --- | --- |
| fully | There is clear evidence from beneficiaries or past projects that delivery of Results will remove the causes of the main problems underlying the Project Purpose. |
| fairly | Delivery of Results seems likely to remove the causes of the main problems underlying the Project Purpose, but little evidence is presented. |
| hardly | Delivery of Results will remove some of the causes of the main problems underlying the Project Purpose, but no evidence is presented. |
| Not at all | Results do not address the causes of the main problems underlying the Project Purpose. |

#### Are the means sufficiently justified by quantified objectives

Projects utilise scarce resources, and must therefore be fully justified on economic and financial grounds. Determining the economic and financial viability of a project can be a complicated process, however it should be possible to gain a basic measure of a project’s cost effectiveness by comparing the means to be deployed to the planned achievements of the project (e.g. total cost/person trained; total cost per person employed). Assessment of this criterion therefore requires, firstly, that objectives are fully specified (with Quantity, Quality, Time, Location and Target group); and secondly, that we have sufficient information to compare the cost effectiveness of using resources for this project against alternative uses of the same resources.

Indicators represent a particularly problematic area of project design. Often indicators are specified without Quantity, Quality, Time, Location and Target group, and are often not ‘specific’ to the objective they are intended to measure. For example, if the Project Purpose is ‘improved health status of pregnant and nursing mothers’ an indicator of ‘increased number of pregnant and nursing mothers receiving treatment’ is not specific to the objective as it measures service delivery. A specific indicator would be ‘reduced incidence of under-nutrition among pregnant and nursing mothers’. Quantity, location and time would then be added to complete the indicator. Key indicators should where appropriate be disaggregated by gender.

##### Scoring indicators: The means are justified by quantified objectives…

|  | when... |
| --- | --- |
| fully | Indicators for Project Purpose and Results are ‘specific’ and are described with measurable target values, time frame, target group, location and quality, if possible. Estimated cost effectiveness is acceptable. |
| fairly | Indicators for Project Purpose and Results are ‘specific’ but are described with incomplete indicators (e.g. no target values). Cost effectiveness cannot be estimated. |
| hardly | Indicators for Project Purpose and Results are not ‘specific’. |
| not at all | No indicators are specified for the Project Purpose or Results. |

#### Have important external conditions been identified?

External factors (or assumptions) are the factors that may be important for the success of the project but which it chooses not to, or is unable to, control. They include accompanying actions by other organisations (e.g. the government or other projects). In the logframe these external factors are formulated as assumptions, and are specified at the levels of Activities, Results and Project Purpose. As the assumptions are important to project success, they must be monitored during the project’s lifetime, and must therefore be formulated in measurable terms. Risk analysis identifies these assumptions and assesses the likelihood that they will be realised.

Assumptions will be identified from the problem analysis, from previous experience, from assessment of sustainability, and from common sense. Common problems are that assumptions are added as an afterthought, and that problem analysis has not been thorough, leading to poor specification of assumptions.

##### Scoring indicators: Important external conditions have been identified...

|  | when... |
| --- | --- |
| fully | External conditions and accompanying measures have been comprehensively identified at the relevant levels. |
| fairly | External conditions and accompanying measures have been identified, but gaps remain. |
| hardly | Some external conditions and accompanying measures have been identified, but many important factors appear to have been left out. |
| not at all | External conditions and accompanying measures are hardly mentioned. |

#### Is the probability of realisation of the Assumptions acceptable?

When the external factors have been identified, we can check whether the probability of realisation is discussed in the proposal. This aspect will be a central part of any feasibility study, but unfortunately very little of this information ends up in proposals. Therefore, it becomes difficult to judge this important part of feasibility.

##### Scoring indicators: The probability of realisation of the assumptions is acceptable…

|  | when... |
| --- | --- |
| fully | For each external condition, supporting evidence is provided that the probability of realisation is acceptable. |
| fairly | For most external conditions, supporting evidence is provided that the probability of realisation is acceptable. |
| hardly | For some external conditions, supporting evidence is provided that the probability of realisation is acceptable. |
| not at all | No supporting evidence regarding the probability of realisation of external conditions is presented, and doubts exist as to whether they can be realised. |

#### Will the implementing agencies be able to implement the project?

If the logic makes sense and the risks are acceptable, it is still important to assess whether the implementing agencies will be able to realise all the works if provided with the necessary means. In order to be able to do this, detailed information regarding the organisational design, the management, the procedures and the means are needed, which is described as the contents of chapter 5 - ‘Implementation’ - of the basic format (PCM Manual page 53-54). Information regarding the track record of implementing agencies is also useful for assessing organisational capacity. The active involvement of implementing agencies in the formulation phase of the project is a positive factor as it indicates ownership, and is likely to mean that expectations of implementing agency capabilities are more realistic.

##### Scoring indicators: Implementing agencies are likely to be able to implement the project…

|  | when... |
| --- | --- |
| fully | Responsibilities and procedures have been clearly established, the implementing agencies have actively participated in the formulation phase and have relevant implementing experience. |
| fairly | Responsibilities and procedures have been defined for most Results, and at least one of the remaining aspects above mentioned has been described. |
| hardly | Only one of the above mentioned aspects has been described. |
| not at all | No responsibilities and procedures are mentioned for the Results, no information regarding implementing agencies is provided. |

### Sustainability

Sustainability can be described as the degree to which the benefits which are produced by the project for the beneficiaries continue after the project has been completed.

#### Will the relevant authorities have a supportive policy after the project has ended?

No project can be sustained in an unsupportive policy environment. Making the policy environment more supportive may indeed require adapting or changing existing regulations, or even create new legislation.

##### Scoring indicators: Adequate policy support can be expected...

|  | when... |
| --- | --- |
| Fully | Relevant authorities have demonstrated support to projects of this type through the adaptation of rules, regulations and policies, and the commitment of significant resources. |
| Fairly | Relevant authorities have demonstrated support to projects of this type through the adaptation of rules, regulations and policies, but have not committed significant resources. |
| Hardly | Relevant authorities have not yet demonstrated support to projects of this type but have undertaken to adapt rules, regulations and policies, but have not committed significant resources. |
| not at all | No information on policy support is presented. |

#### Is the technology appropriate for the local conditions?

Projects often involve the provision of new technologies to implementing agencies and beneficiaries. Technology refers not just to hardware, but to ‘softer’ items such as new seeds or new methods of applying an existing technology. It is important to determine the appropriateness of this technology to the capabilities and preferences of the target institution and beneficiaries. As different groups (e.g. men and women) are likely to have different views of a particular technology, it is important to disaggregate the information. It is also important to assess whether the operating environment supports the use of the technology (e.g. through availability of spare parts or provision of technical advice) in a sustainable and safe manner (e.g. through the existence of a sound regulatory framework).

##### Scoring indicators: Technology is appropriate for local conditions...

|  | when... |
| --- | --- |
| Fully | Various alternatives have been examined, and in the selection the different needs of the beneficiaries (men and women), local conditions and local capacities have been taken into account. |
| Fairly | The different needs of the beneficiaries (men and women), local conditions and local capacities have been taken into account for the chosen technology, but no alternatives have been examined. |
| Hardly | No alternatives have been examined, and only some of the different needs of the beneficiaries (men and women), local conditions and local capacities have been taken into account. |
| not at all | No alternatives have been examined, none of the different needs of the beneficiaries, local conditions and local capacities have been taken into account. |

#### Will the ecological environment be preserved during and after the project?

A project can only be sustainable if it preserves the natural resources on which it relies. Take for example a project with the purpose of improving the health of a village through increased food production obtained via activities such as irrigation and use of pesticides. Such a project will not be sustainable if water is extracted at a faster rate than it is replenished. Furthermore, if the increased food production is made at the expense of increased pesticide residues in the drinking water and consequent health problems among the villagers, the Project Purpose is defeated and it can not be called sustainable, even if the increased food production is sustained after the end of the project. In other words, a sustainable stream of benefits can only be guaranteed if environmental issues are addressed as part of project design. Projects must ensure that the use of those resources which are input to the project is sustainable, and that the project does not create other environmental problems which counteract the Project Purpose.

##### Scoring indicators: The ecological environment is likely to be preserved after the project…

|  | when… |
| --- | --- |
| Fully | There is evidence that the appropriate level of Environment Assessment has been carried out (check with existing screening lists), and that all necessary recommendations are integrated in project design. This means that an environment management plan which specifies the environmental (mitigating) measures to be undertaken should be in place, as well as a plan for monitoring the environmental situation of the project and for taking further environmental action should the mitigating measures prove insufficient. |
| Fairly | There is evidence that the appropriate level of Environment Impact Assessment has been carried out and that most, but not all, necessary recommendations are integrated in project design. |
| Hardly | No assessment has been carried out, and only some measures are indicated without being founded on an adequate environment analysis. |
| Not at all | No assessment has been carried out but is required on the basis of current procedures. |

#### Will there be adequate ownership of the project by the beneficiaries?

Evaluations of projects demonstrate that ownership of the project by the beneficiaries is often crucial to success, both in terms of feasibility (during the project’s lifetime) and for sustainability (post-project). Ownership can be described as the degree to which beneficiaries feel themselves owners, actors and decision makers in the project. This factor should be addressed in the very early stage of the planning process.

##### Scoring indicators: Ownership of the project by the beneficiaries is likely…

|  | when... |
| --- | --- |
| fully | Beneficiaries took the initiative to promote the initial idea, they have been active participants in all phases of the planning process, and major decisions have been validated by their representatives. |
| fairly | Beneficiaries have expressed positive support for the project and have been consulted during the planning process. |
| hardly | Beneficiaries have been informed in an early stage of the planning process, but not actively involved. |
| not at all | No information regarding consultation is presented. |

#### Will all beneficiaries have adequate access to benefits and production factors during and after the project?

Projects take place in social contexts and have social implications. To achieve sustainable benefits project planners must therefore understand the cultural and social implications of projects, and recognise the differing roles and needs of the different groups likely to be involved in, or affected by, the project. In this way participation is strengthened and prospects for sustainability enhanced. A particular issue is the involvement of women in project implementation and their access to project benefits, but in many contexts the concerns of other particular groups (e.g. indigenous peoples, the disabled, children, etc.) should also be addressed.

##### Scoring indicators: Women and other groups will probably have access to benefits…

|  | when... |
| --- | --- |
| fully | The proposal has analysed the access to potential benefits for different sub-groups of beneficiaries, and specifies in detail how equal access to the benefits will be assured for all beneficiaries. |
| fairly | The proposal indicates a number of measures for ensuring equal access to the resources and benefits for all beneficiaries, but these will not guarantee equality. |
| hardly | The proposal mentions the issue of access, but gives little or no explanation of what measures will be taken to guarantee adequate access. |
| not at all | No mention is made of the issue nor of measures to be taken. |

#### Will the implementing agencies be able to provide follow-up after the project?

Institutional and management capacity of the implementing agencies is important not only during the project’s lifetime (feasibility – see question 2.7), but also after project completion (sustainability). The organisational design of a project should therefore take institutional sustainability into account by selecting those organisations and institutions which have a strong interest in continuing to deliver services post-project, and to ensure that these organisations have the required skills and experience to do so after completion of project funding. A particular issue concerns the choice between public and/or private forms of organisation.

##### Scoring indicators: Implementing agencies are likely to be able to provide follow up…

|  | when... |
| --- | --- |
| fully | The implementing agencies have demonstrated a strong interest in continuing to deliver services post-project, and adequate institution-building measures have been built into the project to enable them to do so. |
| fairly | The implementing agencies have demonstrated interest in continuing to deliver services post-project and some institution-building measures have been built into the project to enable them to do so. |
| hardly | The implementing agencies have not demonstrated interest in continuing to deliver services post-project; or institution-building measures are not adequate to enable them to do so. |
| not at all | None of the above-mentioned aspects is described. |

#### Is the financial and economic analysis reliable? Does it confirm that the ‘incremental project’ is efficient, effective, viable, relevant and that its effects are positive?

It is essential that all relevant entities (i.e. groups incurring costs or receiving benefits as a result of the project) are taken into account and analysed separately. As well, the ‘with project’ and ‘without project’ scenarios should be properly defined and summarised in separate cash flows. Although the type and extent of financial and economic analysis to be performed is adapted to each project, the aim is always to determine whether the incremental benefits of the project outweigh its costs in both financial and economic terms. The analysis should also assess the incremental effects of the project on growth, public funds, foreign exchange and income distribution; and if appropriate international viability (in shadow pricing terms). Assumptions should be clearly stated and realistic, and sensitivity analysis performed to determine their relative importance. In this context, it is important to assess if the data collected by the consultant is reliable (for example by comparing with similar projects). If all benefits and/or costs cannot be valued in monetary terms, then at least an efficiency analysis should be performed, and the financial viability of the project demonstrated. The ‘with project’ scenario should be compared with alternative options which should be adequately quantified and valued. Justification should be provided for why the preferred option has been chosen.

It should be remembered that while financial and economic analysis is a very important element of project preparation, it does not provide the only basis for judging whether a project should go ahead. Projects may provide significant non tangible benefits which cannot be included in any calculation of Net Present Value, or Internal Rate of Return.

##### Scoring indicators: The financial and economic analysis is reliable and confirms that the ‘incremental project’ is efficient, effective, viable, relevant and that its effects are positive…

|  | when… |
| --- | --- |
| fully | All relevant economic entities are identified and analysed separately. The ‘with project’ and ‘without project’ scenarios are fully defined and summarised in separate cash flows. The data used is reliable. Different alternatives were quantified and the selection of the best alternative is described in sufficient detail. The financial and economic analysis performed allows a clear judgement to be made on the incremental project’s efficiency, effectiveness, viability, relevance and effects. |
| fairly | Some relevant economic entities were omitted with justification and the ‘with project’ and ‘without project’ scenarios are defined in acceptable detail, as well as the choice of the best alternative. The financial and economic analysis performed allows a judgement to be made on the incremental project’s efficiency, effectiveness, viability, relevance, and effects, but some important questions remain. |
| hardly | Some relevant economic entities were omitted without justification; the ‘with project’ and ‘without project’ scenarios are not defined in acceptable detail. The financial and economic analysis performed does not allow a judgement on the incremental project’s efficiency, effectiveness, viability and relevance. Many important questions remain and much relevant data is missing. |
| not at all | No financial or economic analysis is presented. |

## Using the Quality Assessment Tool to
Identify Information Needs

- Training and Helpdesk Services for Project Cycle Management

- Training Document

| 1. Relevance |  |
| --- | --- |
| 1.1 Are the beneficiaries clearly identified? | Rating: |
| 1.2 Are the problems of the beneficiaries described sufficiently? | Rating: |
| 1.3 Is the problem analysis sufficiently comprehensive? | Rating: |
| 1.4 Do the Overall Objectives explain why the project is important for society? | Rating: |
| 1.5 Is the Project Purpose defined in terms of benefits to the beneficiaries? | Rating: |
| 1.6 Has the need for the Results been demonstrated? | Rating: |
| 2. Feasibility |  |
| 2.1 Will the Project Purpose contribute to the Overall Objectives (if the Assumptions hold)? | Rating: |
| 2.2 Are the Results described as services to be delivered to the target group? | Rating: |
| 2.3 Will the Project Purpose be achieved if the Results were delivered? | Rating: |
| 2.4 Are the means sufficiently justified by quantified objectives? | Rating: |
| 2.5 Have important external conditions been identified? | Rating: |
| 2.6 Is the probability of realisation of the Assumptions acceptable? | Rating: |
| 2.7 Will the implementing agencies be able to implement the project? | Rating: |
| 3. Sustainability |  |
| 3.1 Will the relevant authorities have a supportive policy after the project has ended? | Rating: |
| 3.2 Is the technology appropriate for the local conditions? | Rating: |
| 3.3 Will the ecological environment be preserved during and after the project? | Rating: |
| 3.4 Will there be adequate ownership of the project by the beneficiaries? | Rating: |
| 3.5 Will all beneficiaries have adequate access to benefits and production factors | Rating: |
| during and after the project? |  |
| 3.6 Will the implementing agencies be able to provide follow-up after the project? | Rating: |
| 3.7 Is the financial and economic analysis reliable? Does it confirm that the 'incremental | Rating: |
| project' is efficient, effective, viable, relevant and that its effects are positive? |  |

## Quality Rating Sheet for Financing Proposals

- Training and Helpdesk Services for Project Cycle Management

- Training Document

| Project title: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Analyst: |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |
|  |  |  | fully | fairly | hardly | not at all |
| 1. | Relevance |  |  |  |  |  |
| 1.1 | Are the beneficiaries clearly identified? |  |  |  |  |  |
| 1.2 | Are the problems of the beneficiaries described sufficiently? |  |  |  |  |  |
| 1.3 | Is the problem analysis sufficiently comprehensive? |  |  |  |  |  |
| 1.4 | Do Overall Objectives explain why the project is important for society? |  |  |  |  |  |
| 1.5 | Is the Project Purpose defined in terms of benefits to the beneficiaries? |  |  |  |  |  |
| 1.6 | Has the need for the Results been demonstrated? |  |  |  |  |  |
| 2. | Feasibility |  |  |  |  |  |
| 2.1 | Will the Project Purpose contribute to the Overall Objectives? |  |  |  |  |  |
| 2.2 | Are Results described as services to be delivered to the target group? |  |  |  |  |  |
| 2.3 | Will the Project Purpose be achieved if the Results were delivered? |  |  |  |  |  |
| 2.4 | Are the means sufficiently justified by quantified objectives? |  |  |  |  |  |
| 2.5 | Have important external conditions been identified? |  |  |  |  |  |
| 2.6 | Is the probability of realisation of the Assumptions acceptable? |  |  |  |  |  |
| 2.7 | Will the implementing agencies be able to implement the project? |  |  |  |  |  |
| 3. | Sustainability |  |  |  |  |  |
| 3.1 | Will the relevant authorities provide policy support after project completion? |  |  |  |  |  |
| 3.2 | Is the technology appropriate for the local conditions? |  |  |  |  |  |
| 3.3 | Will the ecological environment be preserved during and after the project? |  |  |  |  |  |
| 3.4 | Will there be adequate ownership of the project by the beneficiaries? |  |  |  |  |  |
| 3.5 | Will all beneficiaries have adequate access to benefits and production factors during and after the project? |  |  |  |  |  |
| 3.6 | Will the implementing agencies be able to provide follow-up after the project? |  |  |  |  |  |
| 3.7 | Is the financial and economic analysis reliable? Does it confirm that the 'incremental project' is efficient, effective, viable, relevant and that its effects are positive? |  |  |  |  |  |

The tool used to integrate environmental aspects like the above in project preparation and implementation is called Environmental Impact Assessment – EIA. There are specific instructions and guidelines for when and how to apply EIA, based on the collective experience of donors and partners regarding common impacts of typical projects.

The incremental project refers to the flows with project minus flows without project.

Efficiency – comparison of the results obtained with the resources used;

Effectiveness – comparison of the project’s purpose with its results;

Viability – i) the solvency of the project during its lifetime; and ii) whether net benefits will continue to flow after project completion;

Relevance – the extent to which the project fits with and contributes to the economic and structural reform objectives of partner country and the EU.

Financial: form the point of view of individual entities or group of entities (micro level)

Economic: from the point of view of the Nation (macro level)